## Gannt
Logistics team tasks for the community
Tasks per team | Details | Action | Who | Completion date
Venue
Select members | Josephine (leader), Chris, Ben, Ria | Done
Secure lease | ACP to sign lease of hall | Done
Repairs to hall | Building on council's books now, list of repairs given to council, council sitting this Friday (28/01/05) – decisions need to be made by officials from several depts. Contact has estimated 3 weeks to complete repairs: end Feb agreed verbally. Tasks TBD to obtain approval to use building will be done, and others for the creche completed at a later date. | Call contact over weekend to discuss meeting outcome | Josephine | 2005-02-03
Furniture at hall? | Existing furniture is unsuitable and will be throw out. | TBD
Hire furniture | Will revisit in early March: one quote already obtained. | Confirm vendor and arrange | Josephine | 2005-03-07
Alcohol license | Estimated to be R250 | Get license fee, terms and lead time on obtaining the license from the council | Chris | 2005-02-03
|  | Obtain license | Josephine | 2005-03-01
Council approval | Need details of this. | Clarify what needs to be done to gain council approval for the event | Josephine | 2005-02-03
Obtain electrician | Need a local, certified electrician to be on standby during the Fiesta. Idea is to invite several candidates to next meeting and see who is most suitable: a discount on their services will be asked for. | Contact local electricians | Barnard | 2005-02-03
Security
Select members | Bernard (leader) | Done
Number of guards | Three shifts of 10 hours each, with 5 guards per shift, estimate of R20/hr per guard is ok, may need one extra for parking. New est is R1200. Community Crime Prevention Service (a local NGO staffed with volunteers)
Venue security | Building needs to looked at in detail to determine security risks | Review building for security holes | Barnard, with help from Josephine | 2005-03-01
Car park security | Decide on parking security once car park area is known | TBD | Barnard | 2005-03-01
Cleaning
Marketing strategy | Jolenene (leader) | Done
Clean toilets | Need shifts of people prepared to clean the toilets regularly | Prepare timetable and obtain staff | Jolenene | 2005-03-01
Clean venue | Suggested local volunteers (kids) are used and paid cash | List of volunteers | Jolenene | 2005-03-01
Cleaning after event | Suggested local volunteers (kids) are used and paid cash | List of volunteers | Jolenene | 2005-03-01
Communications
Select members | Lilian (leader), Shireen, Whitney (as back up) | Done
Internal communication | Suggested a PC with Internet connection necessary for coordinating team's activities and between other teams, Internet access needed to share info – need PC with Internet connection | Liaise with Alan | Jenni | 2005-02-03
| Comms leader needs PC and Internet connection at home | Lilian to confirm feasibility | Lilian | 2005-02-03
Marketing strategy | Start with a list of all community organisations, including those not on email, local business etc | Prepare list | Lilian | 2005-02-03
Short communique | To be sent to the above list + something to market to potential sponsors | Lilian to prepare this with help from others | Lilian | 2005-02-07
Food and drink
Select members | Julius (leader), Clifford, Christolene, Nicki | Done
Vendors | Julius runs the Grace Feeding Scheme, a local NGO distributing 30,000 meals a month to the day hospitals, schools and HIV/AIDS patients. Will provide meals. Other, small vendors invited in exchange for a small donation | Clarify on menu, hours of sale and equipment required | Julius | 2005-02-07
|  | Clarify organisaitonal details of small vendors | Julius | 2005-02-07
|  | Clarify on donations to what? | Julius | 2005-02-03
Food sponsors | For food stands and small donations: Coca-cola, Pick&Pay, Dairymaid, SAB etc | Contact food sponsors | Julius | 2005-02-03
Beer garden | Decided to rather sell alcohol in a controlled environment rather than allowing it from outside. | Details of area and furniture | Nicki / Julius | 2005-02-07
|  | Rules | Nicki / Julius | 2005-02-07
|  | Liaise with Chris re license | Nicki / Julius | 2005-03-01
Entertainment
Select members | Whitney (leader), Alain, Shafiek | Done
Chose entertainment | List of entertainers enjoyed by local community | Obtain list | Whitney | 2005-02-03
Organize PA system | Two systems decided on: a projector and microphone for demonstrations inside the hall and a full, 5000W system for outside. | Details of systems and prices | Whitney | 2005-02-03
Stand for band | Either trailer borrowed from Coca-cola or local school can provide | Need more details | Whitney / Julius | 2005-02-03
Transport and setup | Details required | TBD
Agreements | TBD